## January 2026
Planning/Zoning Activities as of 1/22/2025
Scheduled Public Hearings | Request Type | Location/Description | Hearing Dates
25-15-SA: Single-Cut Division | Amendment to existing Single-Cut ordinance | Countywide Amendment | Deferred by PC at October 7, 2025, meeting (60 day deferral); approved by PC at Dec. 2, 2025, meeting (4-1); public hearing before BoS on Jan. 26, 2026
25-16-ZA: Minimum Lot Size Reference Chart | Amendment to Minimum Lot Size Reference Chart | Countywide Amendment | Deferred by PC at October 7, 2025, meeting (60 day deferral); approved by PC at Dec. 2, 2025, meeting (4-1); public hearing before BoS on Jan. 26, 2026
25-17-CUP: Super Structures GC Inc | CUP for Automotive Repair, Sales, an Servicing on a 2-acre Commercial zoned property | TM 25-18C, 4601 Anderson Highway | Deferred by PC Nov. 5, 2025, meeting (90 day deferral); public hearing before PC on Feb. 3, 2026
25-19-ZA: Motorsports Park | Amendment to add Motorsports Park as a use allowable by CUP in the A10 zoning distirct | Countywide Amendment | Denied by PC at Dec. 2, 2025, meeting (4-0); hearing before BoS on Jan 26, 2026
25-20-REZ: Berk and Alp LLC | Rezone 7.1 acres from Commercial/Commerce Center to Light Indusstiral (to develop storage units and a wharehouse) | TM 43-34, 43-34A - 1375/1377 Anderson Highway | Approved by PC (4-0) at January 6, 2206, meeting; public hearing before BoS on Jan. 26, 2026
25-21-REZ: Lighthouse Learning Academy | Rezoning from I-1 to CC for a private school | 42E-1-8 (South Creek) | Approved by PC (4-0) at January 6, 2206, meeting; public hearing before BoS on Jan. 26, 2026
Design Development Pattern Book
26-01-PB | Pattern book for Powhatan Youth Wrestling | 41-55 | Going to PC February 3rd
Other Items
Carnes (SPA) | Site Plan (Warehouse building) | 15-49 | First round comments sent back to developer -- waiting on reply to comments
Foundry (SPA) | Site Plan (Overnight accomodation) | 18-6 | First round comments sent back to developer -- waiting on reply to comments
CP Assets (SPA) | Site Plan (Industrial Warehouse) | 42E-1-9 | Reponse to first round comments received 1/21/2026
Powhatan Gateway (SPA) | Site Plan (Industrial Pads + Residential Development) | 42-74 | SPA received -- need to send comments to developer when ready
25-08-AFD | AFD Application | 61-27J | Recommended for approval at the AFD Committee meeting--waiting on ordinance change to move forward
26-01-AFD Singleton | AFD Application | TM 04-20 | Possible AFD Committee in March
Powhatan Youth Wrestling | Site Plan / Land Disturbance Permit | New Commercial | 2nd Submittal in review
Ridge Road Subdivision | Minor Subdivision | Ridge Road | Revision submitted, now reduced to 10-lots | 10 lots in A-10 zone
Goddard School | Private Daycare | Oakridge Drive; TM 43-29 | Revision submitted to match revised plat | 12,000 sq ft daycare facility located on 2 acres of unimproved land
Royall Connector Road | New Commercial Entrance | Route 60, 1400 feet west of Red Lane Road | Pending Easement Documentation | Driveway connection to existing Royall Pump and Well business.
Evergreen Community Church | New Site Plan for 12,325 sf church | South side of Anderson Hwy at Lower Hill Road | 1st submittal comments sent to applicant
Life Celebration | New Site Plan for 5,500 sf Funeral Home | North side of Anderson Hwy west of Hwy 522 | Pattern Book approved PC, Second submittal Setback revision needed.
Wawa | New Site Plan for 6,000 sf gas station | South side of Anderson Hwy at Stavemill Road | Second submittal comments sent
Schroeder Road Moss Creek Conservation Subdivision site plan/final plat | 13 residential lots, one 77.02 acre open space lot | East side of Schroeder Rd. | First submittal comments sent
Maple Grove Section 8 final plat | 32 lots | Extension of Maple Lake Road | First submittal comments sent
Fighting Creek Phasing plan | mixed use | phasing and review of phase 1 of The Depot | First submittal in review
Land Disturbance Permits in Review | Notes: | Tax Map # | Review Status:
Moseley Road ESC Plans | Land Disturbance Permit | TM 54-34 | 1st Submittal in Review.
Powhatan Gateway | Land Disturbance Permit | TM 42-74 | 1st Submittal in Review.
Habitat for Humanity - Koinonia Pines Section 1 & 2 | Land Disturbance Permit / Subdivision Construction Plans | TM 23-34 | 2nd Submittal in Review.
Moss Creek Subdivision | Land Disturbance Permit / Subdivision Construction Plans | TM 52-52, 52-53, 52-54 | 2nd Submittal in Review.
Sally Creek Trail - Private Road | Land Disturbance Permit / Subdivision Construction Plans | TM 37-11 | Comments sent. Waiting on Plan Resubmittal.
Gobblers Woods Subdivision | Land Disturbance Permit / Subdivision Construction Plans | TM 23-48 | Comments sent. Waiting on Plan Resubmittal.
Life Celebration | Land Disturbance Permit | TM 26-27 | Comments sent. Waiting on Plan Resubmittal.
Jefferson Industrial Park - Lot 1 | Land Disturbance Permit | TM 51-49 | Waiting on Plan Resubmittal.
Powhatan County Parks & Rec Trail Expansion | Land Disturbance Permit |  | 1st Submittal in Review.
ADA Trail Improvements at Fighting Creek | Environmental Review |  | Working with County Staff to Complete Env. Review
Permitted Land Disturbance Sites | Notes:
Subdivisions:
Maple Grove - Section 7 & 8 | Asphalt road surface installed. Site fully stabilized.
Greywalls - Section 4 | Asphalt road surface installed. Site fully stabilized.
Meadow Grove | Asphalt road surface installed. Site fully stabilized.
Huntington - Section F & G | Gravel road base installed. Site temporarily stabilized.
Walnut Creek - Section 7 | Gravel road base installed. Site temporarily stabilized.
Watkins Mill - Sections 5 & 6 | Gravel road base installed. Site temporarily stabilized.
Hidden Springs (Manakin Woods) | Waiting on Pre-Con Meeting.
Fine Creek Manor | Waiting on construction to begin.
Depot at Fighting Creek | Awaiting contractor to contiune site work. DEQ issues resolved.
Commercial:
Powhatan Self Storage | Waiting on Pre-Con Meeting.
Morris Industries Laydown Yard - Church Road | Waiting on Pre-Con Meeting.
AutoZone | Waiting on Pre-Con Meeting.
Southside Electric Coop - Facility Improvements / Laydown Yard | Monitoring site.
Goochland Powhatan Community Services | Monitoring site.
Goddard School | Site work on hold.
RJ Wade Office/Warehouse | Site work on hold.
Royall Connector Road | Site near completion.
South Creek Office/Warehouse | Site near completion.
Exact Stormwater Management | Site fully stabilized. Waiting on permanent structures to be installed.
Solar Projects:
Quillwart Solar | At final stabilization. Site responabilities transferred to Dominion Energy from DEPCOM power
Northridge Solar | Conversion of sediment basins to stormwater BMPs. Site responabilities transferred to Dominion Energy from DEPCOM power
Beldale Solar | Site work paused by Dominion Energy pending review of wetlands on site.